## Lead
ERP System for College Management
Group Number - 1
Team Lead- Abhishek Yadav
Java FSD

## Status Track
Project Status Check Report Team - 1
Sl no. | Employee ID | Name | Domain | Module | 20-03-2024(Assigned modules) | 21-03-2024(Created models and services) | 22-03-2024(Created Cotrollers and tested ) | 23-03-2024(Created frontend pages) | 24-03-2024(Unit and Manual Testing) | 25-03-2024(Final Integration) | 26-03-2024(PPT creation) | 27-03-2024(Evaluation)
1 | 2587619 | Abhisek Dhal | JAVA FSD | Student Login and Registration and dashboard | Completed Assigning of Modules | Identified fields and create models and services | Created controllers and test using Junit and API testing | Created Student( login, signup and dashboard ) | Unit Testing and manual testing by giveng edge cases | Final integration and integration testing | Final Discussion and improvents and PPT creation | Evaluation
2 | 2587525 | Abhishek Yadav | JAVA FSD | Admin(Faculty, Librarian, Reports) and Event | Completed Assigning of Modules | Identified fields and create models and services | Created controllers and test using Junit and API testing | Event page and Admin(Faculty, Librarian, Reports) | Unit Testing and manual testing by giveng edge cases | Final integration and integration testing | Final Discussion and improvents and PPT creation | Evaluation
3 | 2587401 | Bethala Sai Krishna | JAVA FSD | Faculty Login, Faculty Dashboard | Completed Assigning of Modules | Identified fields and create models and services | Created controllers and test using Junit and API testing | Created Faculty( login, dashboard and other componets ) | Unit Testing and manual testing by giveng edge cases | Final integration and integration testing | Final Discussion and improvents and PPT creation | Evaluation
4 | 2586874 | Akumalla Anjani Shehanaj | JAVA FSD | Faculty add reports and marksheet | Completed Assigning of Modules | Identified fields and create models and services | Created controllers and test using Junit and API testing | Created Faculty( add students, marksheets and other componets ) | Unit Testing and manual testing by giveng edge cases | Final integration and integration testing | Final Discussion and improvents and PPT creation | Evaluation
5 | 2586967 | Ameersohil S Madalmatti | JAVA FSD | Admin Login, Signup and Admin self ops | Completed Assigning of Modules | Identified fields and create models and services | Created controllers and test using Junit and API testing | Created Admin( login, dashboard and student admin) | Unit Testing and manual testing by giveng edge cases | Final integration and integration testing | Final Discussion and improvents and PPT creation | Evaluation
6 | 2587221 | Anuj Kumar Gupta | JAVA FSD | Student module, Student fees and home page | Completed Assigning of Modules | Identified fields and create models and services | Created controllers and test using Junit and API testing | Created Student( results, fees payment and other components ) | Unit Testing and manual testing by giveng edge cases | Final integration and integration testing | Final Discussion and improvents and PPT creation | Evaluation
7 | 2587393 | Archana P | JAVA FSD | Librarian book assign, delete assignment, list assignments | Completed Assigning of Modules | Identified fields and create models and services | Created controllers and test using Junit and API testing | Created Librarian login and books( add, delete and update) | Unit Testing and manual testing by giveng edge cases | Final integration and integration testing | Final Discussion and improvents and PPT creation | Evaluation
8 | 2587808 | B Dheeraj | JAVA FSD | Libraian login, All books listed, add amd delete boook | Completed Assigning of Modules | Identified fields and create models and services | Created controllers and test using Junit and API testing | Created book assignment(list, assign and delete) about page | Unit Testing and manual testing by giveng edge cases | Final integration and integration testing | Final Discussion and improvents and PPT creation | Evaluation

## Status Meeting
Status Meeting Group - 1
| Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
| 2024-03-20 | 9:30 |  | 14:30 |  | 17:30 | a
| 2024-03-21 | 11:00 | a | 13:30 | a | 17:30 | a
| 2024-03-22 | 11:30 | a | 14:30 | a | 18:30 | a
| 2024-03-23 | 11:00 | a | 14:00 | a | 18:30 | a
| 2024-03-24 | 10:00 | a | 13:00 | a | 17:30 | a
| 2024-03-25 | 11:30 | a | 14:00 | a | 17:30 | a
| 2024-03-26 | 11:30 | a | 13:30 | a | 17:30 | a