## Lead
ERP System for College Management Group Number - 1 Team Lead & Frontend Lead- Abhishek Yadav Backend Lead - Abhishek Yadav

## Status Track
Project Status Check Report Team - 1
| Sl no. | Employee ID | Name | Domain | Module | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27
| 1 | 2587619 | Abhishek Dhal | Back-end and Frontend | Student | ER Diagram ,Database, Student components and models | student model, service and controllers | Service, Controller, Exception | Exceptions, Test and Integration of backend, Student Login Page | Added footer component, result page design | API testing and Junit Testing | Final Integration and PPT creation
| 2 | 2587525 | Abhishek Yadav (Team Lead) | Back-end and Frontend | Admin and Event | ER Diagram ,Database, Admin components and models | admin model, services and controllers | Service, Controller, Exception | Exceptions, Test and Integration of backend, Create frontend Project and navbar | admin login page faculty operations, Intergration | API testing and Junit Testing | Final Integration and PPT creation
| 3 | 2587401 | Bethala Sai Krishna | Back-end and Frontend | Faculty and marksheet | ER Diagram ,Database, Faculty components and models | faculty model, services and controllers | Service, Controller, Exception | Exceptions, Test and Integration of backend, Faculty Login page | Faculty all operation related to students | API testing and Junit Testing | Final Integration and PPT creation
| 4 | 2586874 | Akumalla Anjani Shehanaj | Back-end and Frontend | Faculty | ER Diagram ,Database, Faculty Components and models | librarian model, services and controllers | Service, Controller, Exception | Exceptions, Test and Integration of backend, Faculty Dashboard | Faculty all operations for result add to students | API testing and Junit Testing | Final Integration and PPT creation
| 5 | 2586967 | Ameersohil S Madalmatti | Back-end and Frontend | Admin | ER Diagram ,Database, Navbar and admin components and models | admin model, services and controllers | Service, Controller, Exception | Exceptions, Test and Integration of backend, Add Homepage component | Add Homepage component, admin dashboard with services | API testing and Junit Testing | Final Integration and PPT creation
| 6 | 2587221 | Anuj Kumar Gupta | Back-end and Frontend | Student and fees | ER Diagram ,Database, Student module and models | student model,services and controllers | Service, Controller, Exception | Exceptions, Test and Integration of backend, Student Signup Page | Student Dashboard and fees submission form for students | API testing and Junit Testing | Final Integration and PPT creation
| 7 | 2587393 | Archana P | Back-end and Frontend | Librarian and About | ER Diagram ,Database, Librarian Components and models | librarian model,services and controllers | Service, Controller, Exception | Exceptions, Test and Integration of backend, Librarian Login page | add all components related to view all books | API testing and Junit Testing | Final Integration and PPT creation
| 8 | 2587808 | B Dheeraj | Back-end and Frontend | Librarian | ER Diagram ,Database, Librarian components and models | faculty model. services and controllers | Service, Controller, Exception | Exceptions, Test and Integration of backend, add librarian dashboard | add all components related to issue book | API testing and Junit Testing | Final Integration and PPT creation

## Status Meeting
Status Meeting Group - 1
| Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
| 2024-03-20 | 9:30 |  | 14:30 |  | 17:30 | a
| 2024-03-21 | 11:00 | a | 13:30 | a | 17:30 | a
| 2024-03-22 | 11:30 | a | 14:30 | a | 18:30 | a
| 2024-03-23 | 11:00 | a | 14:00 | a | 18:30 | a
| 2024-03-24 | 10:00 | a | 13:00 | a | 17:30 | a
| 2024-03-25 | 11:30 | a | 14:00 | a | 17:30 | a
| 2024-03-26 | 11:30 | a | 13:30 | a | 17:30 | a
2024-03-27